Tuesday Tips:  Earned Value Calculations

We have gotten a few training issues regarding Earned Value Calculations being ‘off’.  90% of these issues are cleared up once the calculations behind the fields are understood.  This information holds for 12.1.1. and higher.  This information uses the default column/field labels for the EV fields. Unless stated otherwise, the calculation holds at all levels of the WBS.

Some fields require a baseline, some do not.  If you do not have a baseline, to see the Project Level EV information, you should add the Project Level fields to a sub page so that they can be displayed, as they will not display on the baseline view if a baseline is not present.

BAC:  Baseline at Completion

BAC: (Sum of all the assignment level Actual Cost values for the project) + ETC (Cost) at the time the baseline is recorded. This will include future posted actual costs.

Baseline required:  Yes

BCWS:  Budgeted Cost of Work Scheduled

BCWS:  Sum of the BAC through a point in time.  That point in time is the Project As Of Date, if set, else the current system date.

Baseline required:  Yes

BCWP:  Budgeted Cost of Work Performed (a.k.a EV)

BCWP:  Depends on the Earned Value Calculation Method

Baseline Required: Yes

Earned Value Calculation Method -

- Percent Complete:

Task Level: BCWP = BAC * %Complete

Project Level:  BCWP = Sum of [BCWP] for all Level 1 Tasks

- 0/100:

If % Complete is 100, BCWP = BAC, else BCWP = 0

- 50/50:

If % Complete is > 0 but < 100, BCWP = BAC / 2

If % Complete = 100, BCWP = BAC

If % Complete = 0, then BCWP = 0

- Level of Effort (LOE)

BCWP = BCWS

- Weighted Milestones  - use BCWP Override field – not calculated by Clarity

- Milestone Percent Complete (PC) - use BCWP Override field – not calculated by Clarity

- Apportioned Effort (AE) - use BCWP Override field – not calculated by Clarity

ACWP:  Actual Cost of Work Performed

ACWP:  Sum of the actuals on the project through a point in time.  That point in time is the Project As Of Date, if set, else the current system date.  If you have future posted actuals, they will not be included in this calculation unless your As Of date is at or beyond the last date of posted actuals.

Baseline Required:  No

Detail Task Level:	ACWP = Sum of all assignment Actual Cost values for the task

Summary Task:	ACWP = Sum of ACWP for Child Tasks

Project Level:	ACWP = Sum of ACWP for all Level 1 Summary Tasks

EAC: Estimate at Completion

EAC:  Aggregated Total for the cost of all actuals over time

EAC = ACWP + [(BAC – BCWP) / CPI] where CPI = BCWP / ACWP

Baseline Required: Yes

EAC (T): Estimate at Completion (Cost of Total Effort)

EAC (T) = ACWP + ETC (Cost)

Baseline Required: No

EAC (AT): Estimate at Completion (Atypical)

EAC (AT) = ACWP + (BAC – BCWP)

Baseline Required: Yes

ETC (Cost): Cost of Estimate to Complete

ETC (Cost) = remaining labor cost (ETC * billing rate) + remaining non-labor cost

Baseline Required: No

ETC (AT): Atypical cost of Estimate to Complete

ETC (AT) = BAC – BCWP

Baseline Required: Yes

ETC (T): Typical cost of Estimate to Complete

ETC (T) = (BAC – BCWP) / CPI where CPI = BCWP / ACWP

Baseline Required: Yes

CV: Cost Variance

CV is the amount of what has been accomplished versus what has been spent

CV = BCWP – ACWP

Baseline Required: Yes

SV: Schedule Variance

SV is the amount of work performed versus what is scheduled to date

SV = BCWP - BCWS

Baseline Required: Yes

CPI: Cost Performance Index

CPI is the ratio of work performed to money spent

CPI = BCWP / ACWP

CPI >= 1 -> favorable – at or under budget

CPI < 1 -> unfavorable – over budget

Baseline Required: Yes

SPI: Schedule Performance Index

SPI is the ratio or work performed to work scheduled

SPI =BCWP / BCWS

SPI >= 1 -> favorable – ahead of schedule

SPI < 1 -> unfavorable – behind schedule

Baseline Required: Yes